## Sheet1
Contact | Project Name | Tasks | Date | Day of Week | Duration (hours) | Description
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-15 | Wednesday | 4 | Briefed on AWP7, met with Team and started connecting. Pushed secondment agreement.
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-16 | Thursday | 8 | Sorting out contract, requesting access, Teams access
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-17 | Friday | 8 | Onboarding (signing contract, sorting Revit access)
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-20 | Monday | 4 | Requested SPA laptop, teams admin, read some MTM standards and looked at TOC
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-21 | Tuesday | 8 | Worked with Vicki on MD and schematics, requested PW access
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-22 | Wednesday | 8 | Got SPA address, requested SharePoint access, started OCS coordination, discussed BIM with manager
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-23 | Thursday | 8 | Followed up on SharePoint, coordinated with Mech for MSSB, went through fire package, got EPZ layout.
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-24 | Friday | 6 | UPS and isolation workshop, followed up on DTRS req, queried VT req.
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-28 | Tuesday | 8 | Coordinated TMF columns, looked into lighting structure support, coordinated with fire for pathways
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-29 | Wednesday | 8 | started lighting coordination, contacted structures, coordinated TMF columns, requested EPZ in model,
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-30 | Thursday | 8 | Architect IDR, services coordination meeting, Elec & lighting meeting
WSP AUSTRALIA PTY LIMITED | AWP7 |  | 2023-03-31 | Friday | 8 | Draughting markup, Iso Tx Query, HV yard equipment started