## Sheet1
Contact | Project Name | Project Short Code | Date | User | Duration (hours) | Day of Week | Tasks | Description | Week_Num
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-15 | Kyle Vorster | 4 | Wednesday |  | Briefed on AWP7, met with Team and started connecting. Pushed secondment agreement. | 11
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-16 | Kyle Vorster | 8 | Thursday |  | Sorting out contract, requesting access, Teams access | 11
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-17 | Kyle Vorster | 8 | Friday |  | Onboarding (signing contract, sorting Revit access) | 11
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-20 | Kyle Vorster | 4 | Monday |  | Requested SPA laptop, teams admin, read some MTM standards and looked at TOC | 12
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-21 | Kyle Vorster | 8 | Tuesday |  | Worked with Vicki on MD and schematics, requested PW access | 12
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-22 | Kyle Vorster | 8 | Wednesday |  | Got SPA address, requested SharePoint access, started OCS coordination, discussed BIM with manager | 12
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-23 | Kyle Vorster | 8 | Thursday |  | Followed up on SharePoint, coordinated with Mech for MSSB, went through fire package, got EPZ layout. | 12
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-24 | Kyle Vorster | 6 | Friday |  | UPS and isolation workshop, followed up on DTRS req, queried VT req. | 12
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-28 | Kyle Vorster | 8 | Tuesday |  | Coordinated TMF columns, looked into lighting structure support, coordinated with fire for pathways | 13
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-29 | Kyle Vorster | 8 | Wednesday |  | started lighting coordination, contacted structures, coordinated TMF columns, requested EPZ in model, | 13
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-30 | Kyle Vorster | 8 | Thursday |  | Architect IDR, services coordination meeting, Elec & lighting meeting | 13
WSP AUSTRALIA PTY LIMITED | AWP7 | #awp7 | 2023-03-31 | Kyle Vorster | 8 | Friday |  | Draughting markup, Iso Tx Query, HV yard equipment started | 13