## Sheet1
Contact | Project Name | Tasks | Date | Day of Week | Duration (hours) | Description
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-01 | Wednesday | 6 | Delegated items to Nan, Responded to LXA CRS. Responded to 2 off DTP comments. OCS coordination meeting.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-02 | Thursday | 6 | DTP CRS comments. VT comments raised. Coordination Workshop.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-03 | Friday | 6 | Extracted VT drawings for review, CRS MTM OCS workshop, Actioned workshop items.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-08 | Wednesday | 8 | OHW Meeting (outstanding items), Revizto clashes with RN, Ethan catchup, NV support for delegated tasks. Revit issues.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-10 | Friday | 8 | MTM CRS Workshop (2 off), Revizto workshop with NV, actioned workshop items.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-14 | Tuesday | 8 | Coordinated and modelled Tx yard E&B, Weekly Meeting, Updated Grid AE tray, coordination workshop.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-15 | Wednesday | 8 | Electrical catchup meeting, AWP7 catchup meeting, Grid AE resolved!! Coordination workshop (mini). VT workshop.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-16 | Thursday | 4 | Updated VT Pits and coordinated TMF VT pathways. Minor drawing updates.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-17 | Friday | 8 | Penetration workshop, Serbie comments,
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-21 | Tuesday | 8 | Added slab penotrations (TMF & TWF), coordinated conduits and penos, weekly meeting, Vector lift workshop, E&B recoordinate rail bonds and conduit sizes.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-22 | Wednesday | 8 | Weekly meeting, VT internal pathway update and markup, CRS update and meeting. More E&B coordination.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-23 | Thursday | 8 | Coordinated Mech pathways (particularly roof), Coordinated Server Room, attended OHW meeting.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-24 | Friday | 8 | Revizto issues. Completed VT updates and markup. Arc email quires on locks and conduit penos.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-28 | Tuesday | 4 | Added and circuited TMF Gate Isolators. Mini Revizto workshop. Construction Meeting.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-11-29 | Wednesday | 8 | Revizto issues. Construction meeting action items. Cable tray checking (big task)