## Sheet1
Contact | Project Name | Tasks | Date | Day of Week | Duration (hours) | Description
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-01 | Thursday | 9 | Payed RIW subscription, Coordination Civil for HV Tx
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-02 | Friday | 9 | OCS/HYD IDR, Markup for draughting, Pit location data, landscape coordinate.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-06 | Tuesday | 8 | Updated Existing light locations, Weekly meeting, OCS UPS coordination, Pit in CSR request, HV Yard discussion
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-07 | Wednesday | 8 | Resource Meeting, Construction Meeting, TWF UPS supply document.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-08 | Thursday | 8 | Got verification drawings ready.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-09 | Friday | 8 | RE-coordinated OCS, Fault ratings investigation, Coordinated Pits with civil.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-13 | Tuesday | 10 | Verification comments action. Pole schedule update. Weekly meeting. Structures coordinate. Parafil re-circuit design.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-14 | Wednesday | 8 | Weekly resource meeting, TWF driver path, more OCS coordinate. Lighting Designs assist.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-15 | Thursday | 9 | TWF driver conduits and pits design, Lighting updates and coordination with CSR/Fence, Swell conduit removal.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-16 | Friday | 9 | Updated conduits to new light poles. Added Gen Laydown. Updated tagging. Updated circuiting.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-20 | Tuesday | 7 | Verification form update, Package Set, Circuit rationalization, Doc Set creation, Weekly Meeting
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-06-21 | Wednesday | 3 | OVPD drawings review
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-06-22 | Thursday | 9 | Driver's Path Meeting, Lighting Catwalk removal delegate, TWF rejig delegate, SBS meeting.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-06-23 | Friday | 9 | Site visit to Pakenham East Depot
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-06-27 | Tuesday | 8 | Started MTM CRS comment responses. Fixed TMF stair void services. Setup lighting meeting. Attended Weekly meeting.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-06-28 | Wednesday | 8 | Got into lightning design. Weekly Meeting. CRS lighting comments workshop. Added pathways for TWF pit lights.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-06-29 | Thursday | 8 | Delegated PV Design. SBS coordination meeting. Lightning investigation. Bracing in TMF coordination.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-06-30 | Friday | 9 | Followed up on Lightning system details. Coordinated Riser. Modelled Training room. Updated MSB Cable Tray.