## Sheet1
Contact | Project Name | Tasks | Date | Day of Week | Duration (hours) | Description
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-01 | Tuesday | 8 | Started CRS comments. Checked on RIW status. Informal meetings Hyd and Ethan.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-02 | Wednesday | 8 | Weekly resource meeting. CRS comments address.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-03 | Thursday | 8 | OHW coordination. CRS comments (VT and some MTM).
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-04 | Friday | 8 | MTM CRS comments
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-08 | Tuesday | 8 | Fixed up the OCS Reticulation plan. Re-coordinated OCS. Weekly Meeting.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-09 | Wednesday | 8 | CRS meeting with MTM, and MTM CRS responding.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-10 | Thursday | 8 | Updated yard with MTM meeting comments, investigated JWebb comment, resolved some clashes. Moved building mounted lights to TMWF.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-11 | Friday | 8 | Reduced lights on existing buildings, handed over JWebb comment, organised verification set.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-15 | Tuesday | 8 | CRS comments (VT) and meeting, including document update. Lighting in BBQ area.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-16 | Wednesday | 5 | Engineering Review comments, CRS support.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-16 | Wednesday | 3 | Coordination meeting with some action items.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-17 | Thursday | 4 | Followed up outstanding items with Package Manager. Investigated Shed lighting. Added Fire detection pathway.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-17 | Thursday | 4 | Updated cable tray size in TMF, queried fixing details. Email tasks and outstanding items.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-18 | Friday | 2 | Meetings and discussions around TMF cable tray clearance for forklift.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-18 | Friday | 6 | Coordination with OCS and Civil (still). Checking of yard quantity schedules.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-21 | Monday | 2 | SOW for construction, emails and delegation of design check.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-23 | Wednesday | 2 | Coordination meeting and solar design discussion.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-23 | Wednesday | 6 | CRS comment response, construction demarcation workshop.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-24 | Thursday | 4 | Investigated the existing iso transformer and existing lights to be retained.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-24 | Thursday | 4 | Informal architect coordination, Mech ducts coordination.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-25 | Friday | 1 | Followed up on yard. Got access to Propeller.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-25 | Friday | 7 | Coordinated fire extinguishers and checked coverage (both buildings). Coordinated cable tray solution in TMF with structures.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8303 |  | 2023-08-29 | Tuesday | 2 | Switch IDR meeting, OCS PA length assistance.
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-29 | Tuesday | 6 | Weekly Meeting. Reschedule cable tray workshop,
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-30 | Wednesday | 8 | Cable tray coordinate, Arc TV coordinate, Weekly meeting, GIS training,
WSP AUSTRALIA PTY LIMITED | DPK-32-BSG8301 |  | 2023-08-31 | Thursday | 8 | Metering drawing TMF update, TWF create. Precast panel penetartions review.